## Sheet1
Task Name | Description | Delevery Date | Start Date | Release Version | Number of Days | Status | Developer Name | Comments
Environmental setup for local machine | To setup the essential need of the project like tools etc.. | 2019-11-20 |  | MVP1 | 1 | To Do
Skeleton (Structure) | It denotes the structure of the project. | 2019-11-20 |  | MVP1 |  | To Do
Github repository creation | To store the documents in the Github. | 2019-11-20 |  | MVP1 |  | To Do
Login Page for ERPsystem Mobile App | Create ERP system login page for mobile app . | 2019-11-20 |  | MVP1 |  | To Do
Login Page for ERPsystem Web portal | Create ERP system login page for wep portal. | 2019-11-20 |  | MVP1 |  | To Do
Login Page for ERPsystem Mobile View | Create ERP system login page for mobile view. | 2019-11-20 |  | MVP1 |  | To Do
ERPsystem login page upload to the playstore | To upload the mobile app in play store . | 2019-11-20 |  | MVP1 |  | To Do
ERPsystem Login page for IOS | Create IOS version of ERPsystem login page. | 2019-11-20 |  | MVP1 |  | To Do
Cloud Environment setup for ERPsystem | Cloud environmental setup. | 2019-11-20 |  | MVP1 |  | To Do
Data model creation | This needs to be either postgresql or mongo db | 2019-11-20 |  | MVP1 |  | To Do