## Sheet1
Task No | Task Name | Description | Delevery Date | Start Date | Release Version | Number of Days | Status | Developer Name | Comments 1 | Comments 2 | Comments 3
1 | Environmental setup for local machine | To setup the essential need of the project like tools etc.. | 2019-11-20 | 2019-11-07 | MVP1 | 2 | In Progress | Nisholine
2 | Skeleton (Structure) | It denotes the structure of the project. | 2019-11-20 | 2019-11-07 | MVP1 | 1 | Development Completed | Nisholine | It is only front end , not back end | please plan for new task for back end also
3 | Github repository creation | To store the documents in the Github. | 2019-11-20 | 2019-11-07 | MVP1 | 1 | Development Completed | Nisholine | No comments
4 | Login Page for ERPsystem Mobile App | Create ERP system login page for mobile app . | 2019-11-20 |  | MVP1 |  | To Do
5 | Login Page for ERPsystem Web portal | Create ERP system login page for wep portal. | 2019-11-20 | 2019-11-08 | MVP1 | 1 | Development Completed | Nisholine | No comments
6 | Login Page for ERPsystem Mobile View | Create ERP system login page for mobile view. | 2019-11-20 |  | MVP1 |  | To Do
7 | ERPsystem login page upload to the playstore | To upload the mobile app in play store . | 2019-11-20 |  | MVP1 |  | To Do
8 | ERPsystem Login page for IOS | Create IOS version of ERPsystem login page. | 2019-11-20 |  | MVP1 |  | To Do
9 | Cloud Environment setup for ERPsystem | Cloud environmental setup. | 2019-11-20 |  | MVP1 |  | To Do
10 | Data model creation | This needs to be either postgresql or mongo db | 2019-11-20 |  | MVP1 |  | To Do
11 | Home page UX design - screen 1 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
12 | Home page UX design - screen 2 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
13 | Home page UX design - screen 3 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
14 | Home page UX design - screen 4 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
15 | Home page UX design - screen 5 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
16 | Home page UX design - screen 6 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
17 | Home page UX design - screen 7 | Refer the screenshot tab | 2019-11-30 |  | MVP2 |  | To Do
18 | Home page UX design - screen 1 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
19 | Home page UX design - screen 2 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
20 | Home page UX design - screen 3 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
21 | Home page UX design - screen 4 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
22 | Home page UX design - screen 5 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
23 | Home page UX design - screen 6 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
24 | Home page UX design - screen 7 | Mobile View in Web Online | 2019-12-05 |  | MVP2 |  | To Do
25 | Home page UX design - screen 1 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do
26 | Home page UX design - screen 2 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do
27 | Home page UX design - screen 3 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do
28 | Home page UX design - screen 4 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do
29 | Home page UX design - screen 5 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do
30 | Home page UX design - screen 6 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do
31 | Home page UX design - screen 7 | Mobile App | 2019-12-15 |  | MVP2 |  | To Do

## screenshot
Home page UX design - screen 3 |  |  | Home page UX design - screen 1
Home page UX design - screen 2
| Home page UX design - screen 4 |  |  | Home page UX design - screen 5
Home page UX design - screen 6
Home page UX design - screen 7